## PORTFOLIO REPORT
DIGITAL PORTFOLIO REPORT
Portfolio position ¦ Reporting date 14 September 2026 ¦ Live links to initiative, PEP, cost and control data
TOTAL APPROVED BUDGET |  |  | ACTUAL SPEND |  |  | AVERAGE PLANNED |  |  | AVERAGE ACTUAL |  |  | AT RISK / BLOCKED
8305000 |  |  | 4216000 |  |  | 68.01% |  |  | 56.39% |  |  | 4
Initiative ID | Initiative | Status | Health | Baseline finish | Forecast finish | Planned % | Actual % | Variance | Original budget | Approved change | Total budget | Actual spend | Spend % | Remaining budget | Productivity
DIG-001 | Customer Portal Redesign | In Delivery | On Track | 2026-12-18 | 2026-12-18 | 63.26% | 65% | 1.742% | 580000 | 20000 | 600000 | 333000 | 55.5% | 267000 | 1.1673
DIG-002 | ERP Finance Migration | In Delivery | At Risk (Date) | 2026-10-30 | 2027-01-15 | 84.19% | 58.33% | -25.86% | 920000 | 100000 | 1020000 | 648000 | 63.53% | 372000 | 0.93309
DIG-003 | Cyber Security Uplift | In Delivery | On Track | 2026-11-27 | 2026-11-27 | 71.97% | 81.67% | 9.697% | 500000 |  | 500000 | 339000 | 67.8% | 161000 | 1.1613
DIG-004 | Data Platform Modernisation | In Delivery | At Risk (Budget) | 2027-03-31 | 2027-03-31 | 40.18% | 35% | -5.179% | 1180000 | 200000 | 1380000 | 511000 | 37.03% | 869000 | 0.97778
DIG-005 | Mobile Workforce App | Operational / Live | Live | 2026-08-28 | 2026-08-28 | 100% | 100% | 0% | 500000 |  | 500000 | 489000 | 97.8% | 11000 | 1.0227
DIG-006 | CRM Consolidation | In Delivery | At Risk (Date) | 2026-12-04 | 2027-02-12 | 73% | 45% | -28% | 850000 | 75000 | 925000 | 428000 | 46.27% | 497000 | 0.99126
DIG-007 | Cloud Landing Zone | Operational / Live | Live | 2026-07-31 | 2026-07-31 | 100% | 100% | 0% | 450000 |  | 450000 | 444000 | 98.67% | 6000 | 1.0145
DIG-008 | Digital Records Programme | Mobilising | On Track | 2027-05-28 | 2027-05-28 | 14.29% | 13.33% | -0.9524% | 680000 |  | 680000 | 100000 | 14.71% | 580000 | 0.86957
DIG-009 | Service Desk Automation | In Delivery | On Track | 2026-11-13 | 2026-11-20 | 74.68% | 73.33% | -1.35% | 460000 | 15000 | 475000 | 303000 | 63.79% | 172000 | 1.1458
DIG-010 | Procurement Analytics | In Delivery | Blocked | 2026-10-16 | 2026-12-11 | 83.07% | 36.67% | -46.4% | 475000 | 30000 | 505000 | 198000 | 39.21% | 307000 | 0.96577
DIG-011 | Identity Access Management | In Delivery | On Track | 2027-01-29 | 2027-01-29 | 43.21% | 45% | 1.79% | 725000 |  | 725000 | 285000 | 39.31% | 440000 | 1.125
DIG-012 | Legacy Application Decommission | Paused (On Hold) | Cancelled / Deferred | 2026-12-18 | 2027-03-26 | 68.33% | 23.33% | -45% | 545000 |  | 545000 | 138000 | 25.32% | 407000 | 0.93814
Illustrative example data for template demonstration; replace source inputs to refresh this report automatically.
EXECUTIVE INSIGHTS
EXECUTIVE ATTENTION
Delivery is 11.6% behind plan overall.
4 initiatives are more than 10 percentage points behind plan.
Portfolio spend is 50.8% of approved budget.
Largest delivery gap: Procurement Analytics (-46.4%).
Formulas:
Baseline finish = IF([TOTAL APPROVED BUDGET]="","",'COWORKER INPUT'!$I5)
Forecast finish = IF([TOTAL APPROVED BUDGET]="","",'COWORKER INPUT'!$J5)

## INITIATIVES
INITIATIVE CONTROL
Initiative ID | Initiative title | Sponsor | Digital Champion | Delivery route | Lifecycle Status | Health | Baseline finish | Forecast finish | Proposed Status / Health change | Digital Lead confirmation | Delivery group | Entry basis | Delivery model | Detailed plan owner | Budget / cost owner | Digital financial reporting basis
DIG-001 | Customer Portal Redesign | Sarah Bennett | Amir Khan | Development Route | In Delivery | On Track | 2026-12-18 | 2026-12-18 |  | Confirmed
DIG-002 | ERP Finance Migration | James Wilson | Priya Shah | Implementation Route | In Delivery | At Risk (Date) | 2026-10-30 | 2027-01-15 | Move forecast finish to 15/01/2027 | Pending
DIG-003 | Cyber Security Uplift | Helen Brooks | Daniel Okafor | Implementation Route | In Delivery | On Track | 2026-11-27 | 2026-11-27 |  | Confirmed
DIG-004 | Data Platform Modernisation | Mark Evans | Sofia Rossi | Development Route | In Delivery | At Risk (Budget) | 2027-03-31 | 2027-03-31 | Increase budget by £120,000 | Pending
DIG-005 | Mobile Workforce App | Laura Chen | Amir Khan | Development Route | Operational / Live | Live | 2026-08-28 | 2026-08-28 |  | Confirmed
DIG-006 | CRM Consolidation | Robert Hayes | Priya Shah | Implementation Route | In Delivery | At Risk (Date) | 2026-12-04 | 2027-02-12 | Move forecast finish to 12/02/2027 | Pending
DIG-007 | Cloud Landing Zone | Helen Brooks | Daniel Okafor | Implementation Route | Operational / Live | Live | 2026-07-31 | 2026-07-31 |  | Confirmed
DIG-008 | Digital Records Programme | Sarah Bennett | Sofia Rossi | Development Route | Mobilising | On Track | 2027-05-28 | 2027-05-28 |  | Confirmed
DIG-009 | Service Desk Automation | James Wilson | Amir Khan | Development Route | In Delivery | On Track | 2026-11-13 | 2026-11-20 |  | Confirmed
DIG-010 | Procurement Analytics | Mark Evans | Priya Shah | Development Route | In Delivery | Blocked | 2026-10-16 | 2026-12-11 | Change health to Blocked | Confirmed
DIG-011 | Identity Access Management | Laura Chen | Daniel Okafor | Implementation Route | In Delivery | On Track | 2027-01-29 | 2027-01-29 |  | Confirmed
DIG-012 | Legacy Application Decommission | Robert Hayes | Sofia Rossi | Implementation Route | Paused (On Hold) | Cancelled / Deferred | 2026-12-18 | 2027-03-26 | Pause pending archive approval | Pending

## PEP
PROJECT EXECUTION PLAN
Planned progress is calculated automatically from baseline start and finish dates using the reporting date. Enter actual progress on activity and variation rows.
Item ID | Initiative ID | Level | Parent ID | Deliverable / activity | Owner | Baseline start | Baseline finish | Forecast finish | Actual % input | Planned % (auto) | Actual % | Variance | Schedule flag | Blocker | Hierarchy check
1 | DIG-001 | Initiative |  | Customer Portal Redesign | Amir Khan | 2026-04-01 | 2026-12-18 | 2026-12-18 |  | 63.26% | 65% | 1.742% | On Plan |  | OK
1.1 | DIG-001 | Milestone | 1 | Deliver solution and transition | Amir Khan | 2026-04-01 | 2026-12-18 | 2026-12-18 |  | 63.26% | 65% | 1.742% | On Plan |  | OK
1.1.1 | DIG-001 | Activity | 1.1 | Discovery and service design | Amir Khan | 2026-04-01 | 2026-06-26 | 2026-06-26 | 75% | 100% | 75% | -25% | Late |  | OK
1.1.2 | DIG-001 | Activity | 1.1 | Portal build and integration | Amir Khan | 2026-06-27 | 2026-09-23 | 2026-09-23 | 65% | 89.77% | 65% | -24.77% | On Plan |  | OK
1.1.3 | DIG-001 | Activity | 1.1 | User acceptance and launch | Amir Khan | 2026-09-24 | 2026-12-18 | 2026-12-18 | 55% | 0% | 55% |  | On Plan |  | OK
2 | DIG-002 | Initiative |  | ERP Finance Migration | Priya Shah | 2026-01-05 | 2026-10-30 | 2027-01-15 |  | 84.19% | 58.33% | -25.86% | Forecast Slip | Legacy data quality delaying migration | OK
2.1 | DIG-002 | Milestone | 2 | Deliver solution and transition | Priya Shah | 2026-01-05 | 2026-10-30 | 2027-01-15 |  | 84.19% | 58.33% | -25.86% | Forecast Slip | Legacy data quality delaying migration | OK
2.1.1 | DIG-002 | Activity | 2.1 | Chart of accounts design | Priya Shah | 2026-01-05 | 2026-04-13 | 2026-04-13 | 80% | 100% | 80% | -20% | Late |  | OK
2.1.2 | DIG-002 | Activity | 2.1 | Data migration and reconciliation | Priya Shah | 2026-04-14 | 2026-07-24 | 2026-10-09 | 55% | 100% | 55% | -45% | Forecast Slip | Legacy data quality delaying migration | OK
2.1.3 | DIG-002 | Activity | 2.1 | Cutover and training | Priya Shah | 2026-07-25 | 2026-10-30 | 2027-01-15 | 40% | 52.58% | 40% | -12.58% | Forecast Slip | Legacy data quality delaying migration | OK
3 | DIG-003 | Initiative |  | Cyber Security Uplift | Daniel Okafor | 2026-03-02 | 2026-11-27 | 2026-11-27 |  | 71.97% | 81.67% | 9.697% | On Plan |  | OK
3.1 | DIG-003 | Milestone | 3 | Deliver solution and transition | Daniel Okafor | 2026-03-02 | 2026-11-27 | 2026-11-27 |  | 71.97% | 81.67% | 9.697% | On Plan |  | OK
3.1.1 | DIG-003 | Activity | 3.1 | Security controls assessment | Daniel Okafor | 2026-03-02 | 2026-05-30 | 2026-05-30 | 90% | 100% | 90% | -10% | Late |  | OK
3.1.2 | DIG-003 | Activity | 3.1 | Endpoint and network hardening | Daniel Okafor | 2026-05-31 | 2026-08-30 | 2026-08-30 | 85% | 100% | 85% | -15% | Late |  | OK
3.1.3 | DIG-003 | Activity | 3.1 | Penetration test and remediation | Daniel Okafor | 2026-08-31 | 2026-11-27 | 2026-11-27 | 70% | 15.91% | 70% | 54.09% | On Plan |  | OK
4 | DIG-004 | Initiative |  | Data Platform Modernisation | Sofia Rossi | 2026-05-04 | 2027-03-31 | 2027-03-31 |  | 40.18% | 35% | -5.179% | On Plan | Specialist resource cost above plan | OK
4.1 | DIG-004 | Milestone | 4 | Deliver solution and transition | Sofia Rossi | 2026-05-04 | 2027-03-31 | 2027-03-31 |  | 40.18% | 35% | -5.179% | On Plan | Specialist resource cost above plan | OK
4.1.1 | DIG-004 | Activity | 4.1 | Target architecture | Sofia Rossi | 2026-05-04 | 2026-08-21 | 2026-08-21 | 45% | 100% | 45% | -55% | Late |  | OK
4.1.2 | DIG-004 | Activity | 4.1 | Cloud data pipelines | Sofia Rossi | 2026-08-22 | 2026-12-12 | 2026-12-12 | 35% | 20.54% | 35% | 14.46% | On Plan | Specialist resource cost above plan | OK
4.1.3 | DIG-004 | Activity | 4.1 | Analytics migration | Sofia Rossi | 2026-12-13 | 2027-03-31 | 2027-03-31 | 25% | 0% | 25% |  | On Plan | Specialist resource cost above plan | OK
5 | DIG-005 | Initiative |  | Mobile Workforce App | Amir Khan | 2026-01-12 | 2026-08-28 | 2026-08-28 |  | 100% | 100% | 0% | On Plan |  | OK
5.1 | DIG-005 | Milestone | 5 | Deliver solution and transition | Amir Khan | 2026-01-12 | 2026-08-28 | 2026-08-28 |  | 100% | 100% | 0% | On Plan |  | OK
5.1.1 | DIG-005 | Activity | 5.1 | Mobile experience design | Amir Khan | 2026-01-12 | 2026-03-28 | 2026-03-28 | 100% | 100% | 100% | 0% | On Plan |  | OK
5.1.2 | DIG-005 | Activity | 5.1 | Application development | Amir Khan | 2026-03-29 | 2026-06-14 | 2026-06-14 | 100% | 100% | 100% | 0% | On Plan |  | OK
5.1.3 | DIG-005 | Activity | 5.1 | Deployment and adoption | Amir Khan | 2026-06-15 | 2026-08-28 | 2026-08-28 | 100% | 100% | 100% | 0% | On Plan |  | OK
6 | DIG-006 | Initiative |  | CRM Consolidation | Priya Shah | 2026-02-02 | 2026-12-04 | 2027-02-12 |  | 73% | 45% | -28% | Forecast Slip | Supplier integration capacity constrained | OK
6.1 | DIG-006 | Milestone | 6 | Deliver solution and transition | Priya Shah | 2026-02-02 | 2026-12-04 | 2027-02-12 |  | 73% | 45% | -28% | Forecast Slip | Supplier integration capacity constrained | OK
6.1.1 | DIG-006 | Activity | 6.1 | Customer data model | Priya Shah | 2026-02-02 | 2026-05-14 | 2026-05-14 | 60% | 100% | 60% | -40% | Late |  | OK
6.1.2 | DIG-006 | Activity | 6.1 | Platform configuration | Priya Shah | 2026-05-15 | 2026-08-25 | 2026-11-03 | 45% | 100% | 45% | -55% | Forecast Slip | Supplier integration capacity constrained | OK
6.1.3 | DIG-006 | Activity | 6.1 | Migration and business rollout | Priya Shah | 2026-08-26 | 2026-12-04 | 2027-02-12 | 30% | 19% | 30% | 11% | Forecast Slip | Supplier integration capacity constrained | OK
7 | DIG-007 | Initiative |  | Cloud Landing Zone | Daniel Okafor | 2026-01-05 | 2026-07-31 | 2026-07-31 |  | 100% | 100% | 0% | On Plan |  | OK
7.1 | DIG-007 | Milestone | 7 | Deliver solution and transition | Daniel Okafor | 2026-01-05 | 2026-07-31 | 2026-07-31 |  | 100% | 100% | 0% | On Plan |  | OK
7.1.1 | DIG-007 | Activity | 7.1 | Network and identity foundation | Daniel Okafor | 2026-01-05 | 2026-03-14 | 2026-03-14 | 100% | 100% | 100% | 0% | On Plan |  | OK
7.1.2 | DIG-007 | Activity | 7.1 | Security guardrails | Daniel Okafor | 2026-03-15 | 2026-05-24 | 2026-05-24 | 100% | 100% | 100% | 0% | On Plan |  | OK
7.1.3 | DIG-007 | Activity | 7.1 | Operational handover | Daniel Okafor | 2026-05-25 | 2026-07-31 | 2026-07-31 | 100% | 100% | 100% | 0% | On Plan |  | OK
8 | DIG-008 | Initiative |  | Digital Records Programme | Sofia Rossi | 2026-08-03 | 2027-05-28 | 2027-05-28 |  | 14.29% | 13.33% | -0.9524% | On Plan |  | OK
8.1 | DIG-008 | Milestone | 8 | Deliver solution and transition | Sofia Rossi | 2026-08-03 | 2027-05-28 | 2027-05-28 |  | 14.29% | 13.33% | -0.9524% | On Plan |  | OK
8.1.1 | DIG-008 | Activity | 8.1 | Records discovery | Sofia Rossi | 2026-08-03 | 2026-11-09 | 2026-11-09 | 25% | 42.86% | 25% | -17.86% | On Plan |  | OK
8.1.2 | DIG-008 | Activity | 8.1 | Retention model design | Sofia Rossi | 2026-11-10 | 2027-02-19 | 2027-02-19 | 10% | 0% | 10% |  | On Plan |  | OK
8.1.3 | DIG-008 | Activity | 8.1 | Repository implementation | Sofia Rossi | 2027-02-20 | 2027-05-28 | 2027-05-28 | 5% | 0% | 5% |  | On Plan |  | OK
9 | DIG-009 | Initiative |  | Service Desk Automation | Amir Khan | 2026-03-16 | 2026-11-13 | 2026-11-20 |  | 74.68% | 73.33% | -1.35% | Forecast Slip |  | OK
9.1 | DIG-009 | Milestone | 9 | Deliver solution and transition | Amir Khan | 2026-03-16 | 2026-11-13 | 2026-11-20 |  | 74.68% | 73.33% | -1.35% | Forecast Slip |  | OK
9.1.1 | DIG-009 | Activity | 9.1 | Process and demand analysis | Amir Khan | 2026-03-16 | 2026-06-04 | 2026-06-04 | 80% | 100% | 80% | -20% | Late |  | OK
9.1.2 | DIG-009 | Activity | 9.1 | Workflow automation | Amir Khan | 2026-06-05 | 2026-08-25 | 2026-09-01 | 75% | 100% | 75% | -25% | Late |  | OK
9.1.3 | DIG-009 | Activity | 9.1 | Knowledge base rollout | Amir Khan | 2026-08-26 | 2026-11-13 | 2026-11-20 | 65% | 24.05% | 65% | 40.95% | Forecast Slip |  | OK
10 | DIG-010 | Initiative |  | Procurement Analytics | Priya Shah | 2026-04-06 | 2026-10-16 | 2026-12-11 |  | 83.07% | 36.67% | -46.4% | Forecast Slip | Source-system access not approved | OK
10.1 | DIG-010 | Milestone | 10 | Deliver solution and transition | Priya Shah | 2026-04-06 | 2026-10-16 | 2026-12-11 |  | 83.07% | 36.67% | -46.4% | Forecast Slip | Source-system access not approved | OK
10.1.1 | DIG-010 | Activity | 10.1 | Spend data ingestion | Priya Shah | 2026-04-06 | 2026-06-09 | 2026-06-09 | 70% | 100% | 70% | -30% | Late |  | OK
10.1.2 | DIG-010 | Activity | 10.1 | Supplier dashboard build | Priya Shah | 2026-06-10 | 2026-08-13 | 2026-10-08 | 30% | 100% | 30% | -70% | Forecast Slip | Source-system access not approved | OK
10.1.3 | DIG-010 | Activity | 10.1 | Business validation | Priya Shah | 2026-08-14 | 2026-10-16 | 2026-12-11 | 10% | 49.21% | 10% | -39.21% | Forecast Slip | Source-system access not approved | OK
11 | DIG-011 | Initiative |  | Identity Access Management | Daniel Okafor | 2026-06-01 | 2027-01-29 | 2027-01-29 |  | 43.21% | 45% | 1.79% | On Plan |  | OK
11.1 | DIG-011 | Milestone | 11 | Deliver solution and transition | Daniel Okafor | 2026-06-01 | 2027-01-29 | 2027-01-29 |  | 43.21% | 45% | 1.79% | On Plan |  | OK
11.1.1 | DIG-011 | Activity | 11.1 | Role catalogue design | Daniel Okafor | 2026-06-01 | 2026-08-20 | 2026-08-20 | 55% | 100% | 55% | -45% | Late |  | OK
11.1.2 | DIG-011 | Activity | 11.1 | Access workflow implementation | Daniel Okafor | 2026-08-21 | 2026-11-10 | 2026-11-10 | 45% | 29.63% | 45% | 15.37% | On Plan |  | OK
11.1.3 | DIG-011 | Activity | 11.1 | Control testing | Daniel Okafor | 2026-11-11 | 2027-01-29 | 2027-01-29 | 35% | 0% | 35% |  | On Plan |  | OK
12 | DIG-012 | Initiative |  | Legacy Application Decommission | Sofia Rossi | 2026-02-16 | 2026-12-18 | 2027-03-26 |  | 68.33% | 23.33% | -45% | Forecast Slip | Archive approval pending | OK
12.1 | DIG-012 | Milestone | 12 | Deliver solution and transition | Sofia Rossi | 2026-02-16 | 2026-12-18 | 2027-03-26 |  | 68.33% | 23.33% | -45% | Forecast Slip | Archive approval pending | OK
12.1.1 | DIG-012 | Activity | 12.1 | Application dependency mapping | Sofia Rossi | 2026-02-16 | 2026-05-28 | 2026-05-28 | 50% | 100% | 50% | -50% | Late |  | OK
12.1.2 | DIG-012 | Activity | 12.1 | Data archive and retention | Sofia Rossi | 2026-05-29 | 2026-09-08 | 2026-12-15 | 20% | 100% | 20% | -80% | Forecast Slip | Archive approval pending | OK
12.1.3 | DIG-012 | Activity | 12.1 | Shutdown and assurance | Sofia Rossi | 2026-09-09 | 2026-12-18 | 2027-03-26 | 0% | 5% | 0% |  |  | Archive approval pending | OK
Formulas:
Schedule flag = IF(OR([Initiative ID]="",[Forecast finish]="",[Actual %]=""),"",IF(AND([Actual %]<1,[Forecast finish]<TODAY()),"Late",IF(AND([Baseline finish]<>"",[Forecast finish]>[Baseline finish]),"Forecast Slip","On Plan")))
Planned % (auto) = IF([Initiative ID]="","",IF([Level]="Initiative","",IF([Level]="Milestone","",IF(OR([Level]="Activity",[Level]="Variation"),IF(OR([Baseline start]="",[Baseline finish]=""),"",IF([Baseline finish]<[Baseline start],"",IF([Baseline finish]=[Baseline start],--(TODAY()>=[Baseline finish]),MAX(0,MIN(1,(TODAY()-[Baseline start])/([Baseline finish]-[Baseline start])))))),""))))

## COST
DIGITAL COST
Initiative ID | Initiative | Cost group | Cost type | Original budget (£) | Additional Approved Budget | Reporting Year | Actual Cost - Jan | Actual Cost - Feb | Actual Cost - Mar | Actual Cost - Apr | Actual Cost - May | Actual Cost - Jun | Actual Cost - Jul | Actual Cost - Aug | Actual Cost - Sept | Actual Cost - Oct | Actual Cost - Nov | Actual Cost - Dec | Actual Cost - Total
DIG-001 | Customer Portal Redesign | Digital Programme Management | Labour | 420000 | 20000 | 2026 | 19600 | 22050 | 24500 | 26950 | 29400 | 29400 | 31850 | 29400 | 31850 | 0 | 0 | 0 | 245000
DIG-001 | Customer Portal Redesign | Digital CTRs | Fees | 160000 | 0 | 2026 | 7040 | 7920 | 8800 | 9680 | 10560 | 10560 | 11440 | 10560 | 11440 | 0 | 0 | 0 | 88000
DIG-002 | ERP Finance Migration | Digital Programme Management | Labour | 680000 | 75000 | 2026 | 37760 | 42480 | 47200 | 51920 | 56640 | 56640 | 61360 | 56640 | 61360 | 0 | 0 | 0 | 472000
DIG-002 | ERP Finance Migration | Digital CTRs | Fees | 240000 | 25000 | 2026 | 14080 | 15840 | 17600 | 19360 | 21120 | 21120 | 22880 | 21120 | 22880 | 0 | 0 | 0 | 176000
DIG-003 | Cyber Security Uplift | Digital Programme Management | Labour | 310000 | 0 | 2026 | 17440 | 19620 | 21800 | 23980 | 26160 | 26160 | 28340 | 26160 | 28340 | 0 | 0 | 0 | 218000
DIG-003 | Cyber Security Uplift | Digital CTRs | Fees | 190000 | 0 | 2026 | 9680 | 10890 | 12100 | 13310 | 14520 | 14520 | 15730 | 14520 | 15730 | 0 | 0 | 0 | 121000
DIG-004 | Data Platform Modernisation | Digital Programme Management | Labour | 760000 | 120000 | 2026 | 25200 | 28350 | 31500 | 34650 | 37800 | 37800 | 40950 | 37800 | 40950 | 0 | 0 | 0 | 315000
DIG-004 | Data Platform Modernisation | Digital CTRs | Fees | 420000 | 80000 | 2026 | 15680 | 17640 | 19600 | 21560 | 23520 | 23520 | 25480 | 23520 | 25480 | 0 | 0 | 0 | 196000
DIG-005 | Mobile Workforce App | Digital Programme Management | Labour | 360000 | 0 | 2026 | 28160 | 31680 | 35200 | 38720 | 42240 | 42240 | 45760 | 42240 | 45760 | 0 | 0 | 0 | 352000
DIG-005 | Mobile Workforce App | Digital CTRs | Fees | 140000 | 0 | 2026 | 10960 | 12330 | 13700 | 15070 | 16440 | 16440 | 17810 | 16440 | 17810 | 0 | 0 | 0 | 137000
DIG-006 | CRM Consolidation | Digital Programme Management | Labour | 590000 | 40000 | 2026 | 22880 | 25740 | 28600 | 31460 | 34320 | 34320 | 37180 | 34320 | 37180 | 0 | 0 | 0 | 286000
DIG-006 | CRM Consolidation | Digital CTRs | Fees | 260000 | 35000 | 2026 | 11360 | 12780 | 14200 | 15620 | 17040 | 17040 | 18460 | 17040 | 18460 | 0 | 0 | 0 | 142000
DIG-007 | Cloud Landing Zone | Digital Programme Management | Labour | 280000 | 0 | 2026 | 22080 | 24840 | 27600 | 30360 | 33120 | 33120 | 35880 | 33120 | 35880 | 0 | 0 | 0 | 276000
DIG-007 | Cloud Landing Zone | Digital CTRs | Fees | 170000 | 0 | 2026 | 13440 | 15120 | 16800 | 18480 | 20160 | 20160 | 21840 | 20160 | 21840 | 0 | 0 | 0 | 168000
DIG-008 | Digital Records Programme | Digital Programme Management | Labour | 450000 | 0 | 2026 | 5520 | 6210 | 6900 | 7590 | 8280 | 8280 | 8970 | 8280 | 8970 | 0 | 0 | 0 | 69000
DIG-008 | Digital Records Programme | Digital CTRs | Fees | 230000 | 0 | 2026 | 2480 | 2790 | 3100 | 3410 | 3720 | 3720 | 4030 | 3720 | 4030 | 0 | 0 | 0 | 31000
DIG-009 | Service Desk Automation | Digital Programme Management | Labour | 335000 | 15000 | 2026 | 17920 | 20160 | 22400 | 24640 | 26880 | 26880 | 29120 | 26880 | 29120 | 0 | 0 | 0 | 224000
DIG-009 | Service Desk Automation | Digital CTRs | Fees | 125000 | 0 | 2026 | 6320 | 7110 | 7900 | 8690 | 9480 | 9480 | 10270 | 9480 | 10270 | 0 | 0 | 0 | 79000
DIG-010 | Procurement Analytics | Digital Programme Management | Labour | 295000 | 0 | 2026 | 8960 | 10080 | 11200 | 12320 | 13440 | 13440 | 14560 | 13440 | 14560 | 0 | 0 | 0 | 112000
DIG-010 | Procurement Analytics | Digital CTRs | Fees | 180000 | 30000 | 2026 | 6880 | 7740 | 8600 | 9460 | 10320 | 10320 | 11180 | 10320 | 11180 | 0 | 0 | 0 | 86000
DIG-011 | Identity Access Management | Digital Programme Management | Labour | 510000 | 0 | 2026 | 16320 | 18360 | 20400 | 22440 | 24480 | 24480 | 26520 | 24480 | 26520 | 0 | 0 | 0 | 204000
DIG-011 | Identity Access Management | Digital CTRs | Fees | 215000 | 0 | 2026 | 6480 | 7290 | 8100 | 8910 | 9720 | 9720 | 10530 | 9720 | 10530 | 0 | 0 | 0 | 81000
DIG-012 | Legacy Application Decommission | Digital Programme Management | Labour | 390000 | 0 | 2026 | 7760 | 8730 | 9700 | 10670 | 11640 | 11640 | 12610 | 11640 | 12610 | 0 | 0 | 0 | 97000
DIG-012 | Legacy Application Decommission | Digital CTRs | Fees | 155000 | 0 | 2026 | 3280 | 3690 | 4100 | 4510 | 4920 | 4920 | 5330 | 4920 | 5330 | 0 | 0 | 0 | 41000

## CONTROL LOG
DELIVERY CONTROL LOG
Control ID | Initiative ID | Type | Description | Owner | Raised date | Due / review date | Position
1 | DIG-002 | Risk | Data migration quality may delay reconciliation | Priya Shah | 2026-07-20 | 2026-09-30 | Escalated
2 | DIG-002 | Action | Complete cleansing of supplier master records | Finance Data Lead | 2026-08-10 | 2026-09-25 | Open
3 | DIG-003 | Evidence requirement | Provide penetration-test closure evidence | Daniel Okafor | 2026-09-01 | 2026-10-09 | Monitoring
4 | DIG-004 | Risk | Specialist engineering rates exceed business case | Sofia Rossi | 2026-08-14 | 2026-09-28 | Escalated
5 | DIG-004 | Decision | Approve additional platform budget | Mark Evans | 2026-09-02 | 2026-09-23 | Open
6 | DIG-006 | Dependency | Supplier interface team availability | Priya Shah | 2026-07-11 | 2026-10-02 | Escalated
7 | DIG-006 | Action | Agree revised phased migration plan | CRM Product Owner | 2026-08-26 | 2026-09-18 | Open
8 | DIG-008 | Assumption | Retention schedules approved by business areas | Sofia Rossi | 2026-08-05 | 2026-10-16 | Monitoring
9 | DIG-009 | Action | Complete knowledge article review | Service Desk Lead | 2026-09-03 | 2026-09-25 | Open
10 | DIG-010 | Issue | Procurement source-system access unavailable | Priya Shah | 2026-08-18 | 2026-09-16 | Escalated
11 | DIG-010 | Decision | Approve interim manual data extract | Mark Evans | 2026-09-07 | 2026-09-17 | Open
12 | DIG-011 | Risk | Role catalogue sign-off may slip | Daniel Okafor | 2026-09-04 | 2026-10-02 | Monitoring
13 | DIG-012 | Dependency | Archive solution approval outstanding | Sofia Rossi | 2026-06-30 | 2026-10-30 | Escalated
14 | DIG-012 | Decision | Confirm restart or closure route | Robert Hayes | 2026-09-01 | 2026-11-06 | Open

## LISTS
CONTROLLED LISTS
Lifecycle Status | Health | Control Position | Delivery Route | PEP Status | Yes / No | Digital Lead Confirmation | PEP Level | Confidence | Control Type | Cost Group | Cost Type | Initiative ID | PEP Initiative Parent IDs | PEP Milestone Parent IDs | PEP No Parent | Entry Basis | Delivery Model | Financial Reporting Basis
Authorised | On Track | Open | Development Route | Open for updates | Yes | Pending | Initiative | High | Action | Digital Programme Management | Labour | DIG-001 | 1 | 1.1 |  | Approved Digital Initiation Form | Development-led delivery | Full budget performance
Mobilising | At Risk (Budget) | Monitoring | Implementation Route | Frozen for reporting | No | Confirmed | Milestone | Medium | Risk | Digital CTRs | Fees | DIG-002 | 2 | 2.1 |  | Approved transition / enterprise mandate | Digital-led implementation / support | Owner-supplied summary
In Delivery | At Risk (Date) | Escalated | Support Route | Approved snapshot | Pending | Rejected | Activity | Low | Assumption | Other |  | DIG-003 | 3 | 3.1 |  | Contract / procurement approval | Vendor-led implementation with Digital client-side assurance | Approved changes / variations only
Adoption / Handover | Blocked | Closed | TBC | Superseded |  | Not required | Variation | Pending confirmation | Issue |  |  | DIG-004 | 4 | 4.1 |  | Leadership instruction | TBC | Emerging cost impacts / exceptions only
Operational / Live | Live | Superseded | [6 empty] | Dependency |  |  | DIG-005 | 5 | 5.1 |  | Existing live project adoption |  | No financial reporting
Paused (On Hold) | Cancelled / Deferred | [7 empty] | Decision |  |  | DIG-006 | 6 | 6.1 |  | Exception entry — authority not evidenced |  | TBC
Closed / Retired | Closed | [7 empty] | Change |  |  | DIG-007 | 7 | 7.1 |  | TBC
[9 empty] | Evidence requirement |  |  | DIG-008 | 8 | 8.1
[12 empty] | DIG-009 | 9 | 9.1
[12 empty] | DIG-010 | 10 | 10.1
[12 empty] | DIG-011 | 11 | 11.1
[12 empty] | DIG-012 | 12 | 12.1

## COWORKER INPUT
COWORKER INPUT
Reporting date | Initiative ID | Initiative | Status | Health | Planned % | Actual % | Variance | Baseline finish | Forecast finish | Late items | Open controls | PEP hierarchy issues | Proposed change | Digital Lead confirmation | Original labour budget | Approved labour change | Approved labour budget | Actual labour cost | Labour variance | Labour % spent | Original fees budget | Approved fees change | Approved fees budget | Actual fees cost | Fees variance | Productivity ratio | Delivery group | Entry basis | Delivery model | Detailed plan owner | Budget / cost owner | Digital financial reporting basis
2026-09-14 | DIG-001 | Customer Portal Redesign | In Delivery | On Track | 63.2576 | 65 | 1.7424 | 2026-12-18 | 2026-12-18 | 1 | 0 | 0 |  | Confirmed | 420000 | 20000 | 440000 | 245000 | 195000 | 55.68% | 160000 | 0 | 160000 | 88000 | 72000 | 1.1673
2026-09-14 | DIG-002 | ERP Finance Migration | In Delivery | At Risk (Date) | 84.1924 | 58.3333 | -25.8591 | 2026-10-30 | 2027-01-15 | 1 | 2 | 0 | Move forecast finish to 15/01/2027 | Pending | 680000 | 75000 | 755000 | 472000 | 283000 | 62.52% | 240000 | 25000 | 265000 | 176000 | 89000 | 0.93309
2026-09-14 | DIG-003 | Cyber Security Uplift | In Delivery | On Track | 71.9697 | 81.6667 | 9.697 | 2026-11-27 | 2026-11-27 | 2 | 1 | 0 |  | Confirmed | 310000 | 0 | 310000 | 218000 | 92000 | 70.32% | 190000 | 0 | 190000 | 121000 | 69000 | 1.1613
2026-09-14 | DIG-004 | Data Platform Modernisation | In Delivery | At Risk (Budget) | 40.1786 | 35 | -5.1786 | 2027-03-31 | 2027-03-31 | 1 | 2 | 0 | Increase budget by £120,000 | Pending | 760000 | 120000 | 880000 | 315000 | 565000 | 35.8% | 420000 | 80000 | 500000 | 196000 | 304000 | 0.97778
2026-09-14 | DIG-005 | Mobile Workforce App | Operational / Live | Live | 100 | 100 | 0 | 2026-08-28 | 2026-08-28 | 0 | 0 | 0 |  | Confirmed | 360000 | 0 | 360000 | 352000 | 8000 | 97.78% | 140000 | 0 | 140000 | 137000 | 3000 | 1.0227
2026-09-14 | DIG-006 | CRM Consolidation | In Delivery | At Risk (Date) | 73 | 45 | -28 | 2026-12-04 | 2027-02-12 | 1 | 2 | 0 | Move forecast finish to 12/02/2027 | Pending | 590000 | 40000 | 630000 | 286000 | 344000 | 45.4% | 260000 | 35000 | 295000 | 142000 | 153000 | 0.99126
2026-09-14 | DIG-007 | Cloud Landing Zone | Operational / Live | Live | 100 | 100 | 0 | 2026-07-31 | 2026-07-31 | 0 | 0 | 0 |  | Confirmed | 280000 | 0 | 280000 | 276000 | 4000 | 98.57% | 170000 | 0 | 170000 | 168000 | 2000 | 1.0145
2026-09-14 | DIG-008 | Digital Records Programme | Mobilising | On Track | 14.2857 | 13.3333 | -0.95238 | 2027-05-28 | 2027-05-28 | 0 | 1 | 0 |  | Confirmed | 450000 | 0 | 450000 | 69000 | 381000 | 15.33% | 230000 | 0 | 230000 | 31000 | 199000 | 0.86957
2026-09-14 | DIG-009 | Service Desk Automation | In Delivery | On Track | 74.6835 | 73.3333 | -1.3502 | 2026-11-13 | 2026-11-20 | 2 | 1 | 0 |  | Confirmed | 335000 | 15000 | 350000 | 224000 | 126000 | 64% | 125000 | 0 | 125000 | 79000 | 46000 | 1.1458
2026-09-14 | DIG-010 | Procurement Analytics | In Delivery | Blocked | 83.0688 | 36.6667 | -46.4021 | 2026-10-16 | 2026-12-11 | 1 | 2 | 0 | Change health to Blocked | Confirmed | 295000 | 0 | 295000 | 112000 | 183000 | 37.97% | 180000 | 30000 | 210000 | 86000 | 124000 | 0.96577
2026-09-14 | DIG-011 | Identity Access Management | In Delivery | On Track | 43.2099 | 45 | 1.7901 | 2027-01-29 | 2027-01-29 | 1 | 1 | 0 |  | Confirmed | 510000 | 0 | 510000 | 204000 | 306000 | 40% | 215000 | 0 | 215000 | 81000 | 134000 | 1.125
2026-09-14 | DIG-012 | Legacy Application Decommission | Paused (On Hold) | Cancelled / Deferred | 68.3333 | 23.3333 | -45 | 2026-12-18 | 2027-03-26 | 1 | 2 | 0 | Pause pending archive approval | Pending | 390000 | 0 | 390000 | 97000 | 293000 | 24.87% | 155000 | 0 | 155000 | 41000 | 114000 | 0.93814
Formulas:
Reporting date = IF([Initiative ID]="","",TODAY())
Baseline finish = IF([Initiative ID]="","",IFERROR(IF(INDEX(InitiativesTable[Baseline finish],MATCH([Initiative ID],InitiativesTable[Initiative ID],0))=0,"",INDEX(InitiativesTable[Baseline finish],MATCH([Initiative ID],InitiativesTable[Initiative ID],0))),""))
Forecast finish = IF([Initiative ID]="","",IFERROR(IF(INDEX(InitiativesTable[Forecast finish],MATCH([Initiative ID],InitiativesTable[Initiative ID],0))=0,"",INDEX(InitiativesTable[Forecast finish],MATCH([Initiative ID],InitiativesTable[Initiative ID],0))),""))

## Chart Data
Health | Count
On Track | 5
Live | 2
At Risk (Date) | 2
At Risk (Budget) | 1
Blocked | 1
Cancelled / Deferred | 1